## Sheet1
Bug ID | Test Case ID | Module | Test Case Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Assigned To | Written By
BUG_001 | TC_NA_001 | New Account |  | System allows mobile number to start with a space. | Open 'New Account' page, enter ' 01201121914' in mobile number field, click 'Submit'. | Error: Mobile number cannot start with a space. | Accepted without error. | High | High | Open | Developer
BUG_002 | TC_NA_002 | New Account |  | System does not validate blank email field, allowing account creation without an email. | Open 'New Account' page, leave email field blank, click 'Submit'. | Error: Email is required. | Account created without email validation. | Critical | Highest | Open | Developer
BUG_003 | TC_BE_003 | Balance Enquiry |  | System allows letters in account number field without showing an error. | Open 'Balance Enquiry' page, enter 'ABC1200' in account number field, click 'Submit'. | Error: Only numbers are allowed in account number. | No error displayed, request processed incorrectly. | High | High | Open | Developer
BUG_004 | TC_NA_003 | New Account |  | Invalid email format is accepted without an error. | Open 'New Account' page, enter hosny99@gmail.com' in email field, click 'Submit'. | Error: Invalid email format. Please enter a valid email (e.g., user@example.com). | Email accepted without validation. | High | High | Open | Developer
BUG_005 | TC_NA_004 | New Account |  | Email field allows leading space, causing incorrect email storage. | Open 'New Account' page, enter ' hosny99@gmail.com' in email field, click 'Submit'. | Error: Email cannot start with a space. | Email saved with leading space. | Medium | Medium | Open | Developer
BUG_006 | TC_DC_001 | Delete Customer |  | Customer ID field allows submission when blank. | Open 'Delete Customer' page, leave Customer ID field blank, click 'Submit'. | Error: Customer ID is required. | Request processed without Customer ID validation. | Critical | Highest | Open | Developer
BUG_007 | TC_BE_002 | Balance Enquiry |  | Special characters are allowed in account number field. | Open 'Balance Enquiry' page, enter '@124512#' in account number field, click 'Submit'. | Error: Special characters are not allowed in account number. | Request processed with invalid characters. | High | High | Open | Developer
BUG_008 | TC_NA_001 | New Account |  | Mobile number allows non-numeric characters. | Open 'New Account' page, enter 'abcd124512' in mobile number field, click 'Submit'. | Error: Mobile number must contain only digits. | Accepted invalid characters in mobile number. | High | High | Open | Developer
BUG_009 | TC_BE_001 | Balance Enquiry |  | System does not validate blank account number field. | Open 'Balance Enquiry' page, leave account number blank, click 'Submit'. | Error: Account number is required. | Request processed without an account number. | Critical | Highest | Open | Developer
BUG_010 | TC_NA_002 | New Account |  | System crashes when submitting form with blank email and mobile fields. | Open 'New Account' page, leave email and mobile fields blank, click 'Submit'. | Error messages should be displayed for both fields. | System crashes instead of showing error messages. | Critical | Highest | Open | Developer
BUG_011 | TC_TC_Withdraw_Acc_001 | Withdraw |  | there is No withdraw button | Open Manger account , no Withdraw botton | Error : no a withdraw botton | there is no withdraw botton | Critical | Highest | Open | Developer
BUG_012 | TC_change_pass_001 | change password |  | there is No Change password button | Open Manger account , No Change password button | Error :No "change password" botton | Error :No "change password" botton | Critical | Highest | Open | Developer
BUG_013 | TC_Mini_sta_001 | Mini statement |  | system isn't loading the page | Open "mini statement" , enter Account number | error: there will be statements | error: there is no statements | Critical | Highest | Open | Developer
BUG_014 | TC_customer_ID_005 | New Account |  | When entering an invalid Customer ID, the system displays an incorrect error message | 1. Navigate to 'New Account' page 2. Enter an invalid Customer ID 3. Click Submit | System should display an error: "Invalid Customer ID" | System displayed an error: "You are not authorized to Add Account for this Customer" | Medium | High | Open | Developer | Maryem Ayman
BUG_015 | TC_Email_02 | New Customer |  | When entering an invalid email format, the system displays an incorrect error message. | 1. Navigate to 'New Customer' page 2. Enter an invalid email format 3. Click Submit | System should display an error: "Invalid Email Format. | System displayed an error: "Email-ID is not valid" | Low | Medium | Open | Developer
BUG_016 | TC_Account_NO_01 | Balance Enquiry |  | The balance enquiry tab does not respond when clicked. | 1. Navigate to 'Balance Enquiry' page 2. Click on the balance enquiry tab | The system displays the account balance | The tab didn't work | High | High | Open | Developer
BUG_017 | TC_NC_037 | Verify Email | Spaces are not allowed in Email | Inserting an invalid Email (adding a space to the Email) | 1) Enter a invalid Email 2) Press Tab / select other field | Error Message Displayed "Email must not contain spaces" | No Error Messages Displayed |  |  | Open | Developer | Mahmoud Gamal
BUG_018 | TC_NC_039 | Verify Email | Top level domain must not be pure numerical | Inserting an invalid Email (adding an Email with tld is all numbers) | 1) Enter a invalid Email 2) Press Tab / select other field | Error Message Displayed "this is not a valid Email form" | No Error Messages Displayed
BUG_019 | TC_NC_040 | Verify Email | Top level domain last character must not be numerical | Inserting an invalid Email (adding an Email with the first character of tld is a number) | 1) Enter a invalid Email 2) Press Tab / select other field | Error Message Displayed "this is not a valid Email form" | No Error Messages Displayed
| TC_EC_007 | Verify Customer Name | Customer Name is required | Inserting a valid Customer Name | 1) Enter a valid Customer Name 2) Press Tab / select other field | No Error Messages Displayed | Edit Customer Form unreachable
| TC_EC_008 | Verify Customer Name | Customer Name must not be blank | Leaving Customer Name field empty | 1) Click on Customer Name field and leave it empty 2) Press Tab / select other field | Error Message Displayed "Customer Name filed is empty" | Edit Customer Form unreachable | Critical
| TC_EC_009 | Verify Customer Name | Special character are not allowed in Customer Name | Inserting an invalid Customer Name (adding a special character to the Customer Name) | 1) Enter a invalid Customer Name 2) Press Tab / select other field | Error Message Displayed "Customer Name must not contain Special characters" | Edit Customer Form unreachable | Critical
| TC_EC_010 | Verify Customer Name | Numbers are not allowed in Customer Name | Inserting an invalid Customer Name (adding a number to the Customer Name) | 1) Enter a invalid Customer Name 2) Press Tab / select other field | Error Message Displayed "Customer Name must not contain numbers" | Edit Customer Form unreachable | Critical
| TC_EC_011 | Verify Customer Name | First character cannot be a space in Customer Name | Inserting an invalid Customer Name (adding an Customer Name with the first character is a space) | 1) Enter a invalid Customer Name 2) Press Tab / select other field | Error Message Displayed "Customer Name must not contain spaces" | Edit Customer Form unreachable
| TC_CS_006 | Customized Statement | First character cannot be a space in Account No | Inserting an invalid Account No (adding an Account No with the first character is a space) | 1) Enter a invalid Account No 2) Press Tab / select other field | Error Message Displayed "First character cannot be a space in Account No" | No Error Messages Displayed
| TC_CS_008 | Customized Statement | Minimum Transaction Value must not be empty | Leaving Minimum Transaction Value field empty | 1) Click on Minimum Transaction Value field and leave it empty 2) Press Tab / select other field | Error Message Displayed "Minimum Transaction Value filed is empty" | No Error Messages Displayed | Critical
| TC_CS_012 | Customized Statement | First character cannot be a space in Minimum Transaction Value | Inserting an invalid Minimum Transaction Value (adding an Minimum Transaction Value with the first character is a space) | 1) Enter a invalid Minimum Transaction Value 2) Press Tab / select other field | Error Message Displayed "First character cannot be a space in Minimum Transaction Value" | No Error Messages Displayed
| TC_CS_014 | Customized Statement | Number of Transactions must not be empty | Leaving Number of Transactions field empty | 1) Click on Number of Transactions field and leave it empty 2) Press Tab / select other field | Error Message Displayed "Number of Transactions filed is empty" | No Error Messages Displayed
| TC_CS_018 | Customized Statement | First character cannot be a space in Number of Transactions | Inserting an invalid Number of Transactions (adding an Number of Transactions with the first character is a space) | 1) Enter a invalid Number of Transactions 2) Press Tab / select other field | Error Message Displayed "First character cannot be a space in Number of Transactions" | No Error Messages Displayed
| TC_EC_016 | Verify City | City is required | Inserting a valid City | 1) Enter a valid City 2) Press Tab / select other field | No Error Messages Displayed | Edit Customer Form unreachable
| TC_EC_017 | Verify City | City must not be empty | Leaving City field empty | 1) Click on City field and leave it empty 2) Press Tab / select other field | Error Message Displayed "City filed is empty" | Edit Customer Form unreachable
| TC_EC_018 | Verify City | Special character are not allowed in City | Inserting an invalid City (adding a special character to the City) | 1) Enter a invalid City 2) Press Tab / select other field | Error Message Displayed "City must not contain Special characters" | Edit Customer Form unreachable
| TC_EC_019 | Verify City | Numbers are not allowed in City | Inserting an invalid City (adding a Number to the City) | 1) Enter a invalid City 2) Press Tab / select other field | Error Message Displayed "City must not contain Number" | Edit Customer Form unreachable
| TC_EC_020 | Verify City | First character cannot be a space in City | Inserting an invalid City (adding an City with the first character is a space) | 1) Enter a invalid City 2) Press Tab / select other field | Error Message Displayed "First character cannot be a space in City" | Edit Customer Form unreachable
| TC_EC_021 | Verify State | State is required | Inserting a valid State | 1) Enter a valid State 2) Press Tab / select other field | No Error Messages Displayed | Edit Customer Form unreachable
| TC_EC_022 | Verify State | State must not be empty | Leaving State field empty | 1) Click on State field and leave it empty 2) Press Tab / select other field | Error Message Displayed "State filed is empty" | Edit Customer Form unreachable | High
| TC_EC_023 | Verify State | Special character are not allowed in State | Inserting an invalid State (adding a special character to the State) | 1) Enter a invalid State 2) Press Tab / select other field | Error Message Displayed "State must not contain Special characters" | Edit Customer Form unreachable | High
| TC_EC_024 | Verify State | Numbers are not allowed in State | Inserting an invalid State (adding a Number to the State) | 1) Enter a invalid State 2) Press Tab / select other field | Error Message Displayed "State must not contain Number" | Edit Customer Form unreachable | High
| TC_EC_025 | Verify State | First character cannot be a space in State | Inserting an invalid State (adding an State with the first character is a space) | 1) Enter a invalid State 2) Press Tab / select other field | Error Message Displayed "First character cannot be a space in State" | Edit Customer Form unreachable
| TC_EC_026 | Verify PIN | PIN is required | Inserting a valid PIN | 1) Enter a valid PIN 2) Press Tab / select other field | No Error Messages Displayed | Edit Customer Form unreachable
| TC_EC_027 | Verify PIN | PIN must not be empty | Leaving PIN field empty | 1) Click on PIN field and leave it empty 2) Press Tab / select other field | Error Message Displayed "PIN filed is empty" | Edit Customer Form unreachable | High
| TC_EC_028 | Verify PIN | Special character are not allowed in PIN | Inserting an invalid PIN (adding a special character to the PIN) | 1) Enter a invalid PIN 2) Press Tab / select other field | Error Message Displayed "PIN must not contain Special characters" | Edit Customer Form unreachable | High
| TC_EC_029 | Verify PIN | PIN Code must have 6 Digits (Lower than 6) | Inserting an invalid PIN (entering a short PIN) | 1) Enter a invalid PIN 2) Press Tab / select other field | Error Message Displayed "PIN Code must have 6 Digits" | Edit Customer Form unreachable | High
| TC_EC_030 | Verify PIN | PIN Code must have 6 Digits (Higher than 6) | Inserting an invalid PIN (entering a long PIN) | 1) Enter a invalid PIN 2) Press Tab / select other field | Error Message Displayed "PIN Code must have 6 Digits" | Edit Customer Form unreachable | High
| TC_EC_031 | Verify PIN | Characters are not allowed in PIN | Inserting an invalid PIN (adding a character to the PIN) | 1) Enter a invalid PIN 2) Press Tab / select other field | Error Message Displayed "PIN must not contain characters" | Edit Customer Form unreachable | High
| TC_EC_032 | Verify PIN | Spaces are not allowed in PIN | Inserting an invalid PIN (adding a space to the PIN) | 1) Enter a invalid PIN 2) Press Tab / select other field | Error Message Displayed "PIN must not contain spaces" | Edit Customer Form unreachable | High
| TC_EC_033 | Verify PIN | First character cannot be a space in PIN | Inserting an invalid PIN (adding an PIN with the first character is a space) | 1) Enter a invalid PIN 2) Press Tab / select other field | Error Message Displayed "First character cannot be a space in PIN" | Edit Customer Form unreachable | High
| TC_EC_034 | Verify Telephone Number | Telephone Number is required | Inserting a valid Telephone Number | 1) Enter a valid Telephone Number 2) Press Tab / select other field | No Error Messages Displayed | Edit Customer Form unreachable
| TC_EC_035 | Verify Telephone Number | Telephone Number must not be empty | Leaving Telephone Number field empty | 1) Click on Telephone Number field and leave it empty 2) Press Tab / select other field | Error Message Displayed "Telephone Number filed is empty" | Edit Customer Form unreachable | High
| TC_EC_036 | Verify Telephone Number | Special character are not allowed in Telephone Number | Inserting an invalid Telephone Number (adding a special character to the Telephone Number) | 1) Enter a invalid Telephone Number 2) Press Tab / select other field | Error Message Displayed "Telephone Number must not contain Special characters" | Edit Customer Form unreachable | High
| TC_EC_037 | Verify Telephone Number | Characters are not allowed in Telephone Number | Inserting an invalid Telephone Number (adding a character to the Telephone Number) | 1) Enter a invalid Telephone Number 2) Press Tab / select other field | Error Message Displayed "Telephone Number must not contain characters" | Edit Customer Form unreachable | High
| TC_EC_038 | Verify Telephone Number | Spaces are not allowed in Telephone Number | Inserting an invalid Telephone Number (adding a space to the Telephone Number) | 1) Enter a invalid Telephone Number 2) Press Tab / select other field | Error Message Displayed "Telephone Number must not contain spaces" | Edit Customer Form unreachable | High
| TC_EC_039 | Verify Telephone Number | First character cannot be a space in Telephone Number | Inserting an invalid Telephone Number (adding an Telephone Number with the first character is a space) | 1) Enter a invalid Telephone Number 2) Press Tab / select other field | Error Message Displayed "First character cannot be a space in Telephone Number" | Edit Customer Form unreachable | High
| TC_EC_040 | Email | Email is required | Inserting a valid Email | 1) Enter a valid Email 2) Press Tab / select other field | No Error Messages Displayed | Edit Customer Form unreachable | High
| TC_EC_041 | Email | Email must not be empty | Leaving Email field empty | 1) Click on Email field and leave it empty 2) Press Tab / select other field | Error Message Displayed "Email filed is empty" | Edit Customer Form unreachable | High
| TC_EC_042 | Email | Email must contain one @ sign | Inserting an invalid Email (adding an Email without @) | 1) Enter a invalid Email 2) Press Tab / select other field | Error Message Displayed "Email must contain @ sign" | Edit Customer Form unreachable | High
| TC_EC_043 | Email | Email must contain at least one dot "." | Inserting an invalid Email (adding an Email without . ) | 1) Enter a invalid Email 2) Press Tab / select other field | Error Message Displayed "this is not a valid Email form" | Edit Customer Form unreachable | High